## Point Burndown
Burndown Chart: Big Blue's Parking Genie
| Requirements Gathering |  | High-level Design |  | Low-level Design |  | Development |  | Testing |  | Task | Name | Date completed | Type
Date | Tasks left | Expected | Tasks left | Expected | Tasks left | Expected | Tasks left | Expected | Tasks left | Expected | login.html | Joel | 2021-03-10 | h
2021-02-01 | 34 | 34 | 19 | 19 | 8 | 8 | 67 | 67 | 3 | 3 | reserveSpot.html | Joel | 2021-03-10 | h
2021-02-02 | 33 | 33.575 | 19 | 18.7625 | 7 | 7.9 | 67 | 66.1625 | 3 | 2.9625 | map.html | Joel | 2021-03-10 | h
2021-02-03 | 33 | 33.15 | 19 | 18.525 | 7 | 7.8 | 67 | 65.325 | 3 | 2.925 | signUp.html | Joel | 2021-03-09 | h
2021-02-04 | 31 | 32.725 | 19 | 18.2875 | 7 | 7.7 | 67 | 64.4875 | 3 | 2.8875 | Html/Css template | Joel | 2021-03-10 | l
2021-02-05 | 29 | 32.3 | 19 | 18.05 | 7 | 7.6 | 67 | 63.65 | 3 | 2.85 | account.html | Joel | 2021-03-10 | h
2021-02-06 | 28 | 31.875 | 19 | 17.8125 | 7 | 7.5 | 67 | 62.8125 | 3 | 2.8125 | get website template | Joel | 2021-03-03 | l
2021-02-07 | 28 | 31.45 | 19 | 17.575 | 7 | 7.4 | 67 | 61.975 | 3 | 2.775 | outline models | Autumn | 2021-03-03 | l
2021-02-08 | 25 | 31.025 | 19 | 17.3375 | 7 | 7.3 | 67 | 61.1375 | 3 | 2.7375 | set up API | Palani | 2021-03-04 | d
2021-02-09 | 23 | 30.6 | 19 | 17.1 | 7 | 7.2 | 67 | 60.3 | 3 | 2.7 | signUp.html->django | Palani | 2021-03-11 | d
2021-02-10 | 15 | 30.175 | 19 | 16.8625 | 7 | 7.1 | 67 | 59.4625 | 3 | 2.6625 | rough draft models | Autumn | 2021-03-06 | d
2021-02-11 | 12 | 29.75 | 19 | 16.625 | 7 | 7 | 67 | 58.625 | 3 | 2.625 | Update models | Palani | 2021-03-09 | d
2021-02-12 | 11 | 29.325 | 19 | 16.3875 | 7 | 6.9 | 67 | 57.7875 | 3 | 2.5875 | nav/main.html | Joel | 2021-03-15 | h
2021-02-13 | 11 | 28.9 | 19 | 16.15 | 7 | 6.8 | 67 | 56.95 | 3 | 2.55 | Scrum notes for sprint | Lexy | 2021-03-15 | r
2021-02-14 | 11 | 28.475 | 19 | 15.9125 | 7 | 6.7 | 67 | 56.1125 | 3 | 2.5125 | create repo | Palani | 2021-02-02 | l
2021-02-15 | 11 | 28.05 | 19 | 15.675 | 7 | 6.6 | 67 | 55.275 | 3 | 2.475 | added doc outlines | Palani | 2021-02-02 | r
2021-02-16 | 11 | 27.625 | 19 | 15.4375 | 7 | 6.5 | 67 | 54.4375 | 3 | 2.4375 | update todo | Palani | 2021-02-04 | r
2021-02-17 | 11 | 27.2 | 19 | 15.2 | 7 | 6.4 | 67 | 53.6 | 3 | 2.4 | Req Def: intro/context | Joel | 2021-02-04 | r
2021-02-18 | 11 | 26.775 | 19 | 14.9625 | 7 | 6.3 | 67 | 52.7625 | 3 | 2.3625 | Project overview | Autumn | 2021-02-05 | r
2021-02-19 | 11 | 26.35 | 19 | 14.725 | 7 | 6.2 | 67 | 51.925 | 3 | 2.325 | adjusted repo structure | P/J | 2021-02-05 | r
2021-02-20 | 11 | 25.925 | 19 | 14.4875 | 7 | 6.1 | 67 | 51.0875 | 3 | 2.2875 | RD: Users and goals | Joel | 2021-02-06 | r
2021-02-21 | 11 | 25.5 | 19 | 14.25 | 7 | 6 | 67 | 50.25 | 3 | 2.25 | RD: non-funct req | Joel | 2021-02-08 | r
2021-02-22 | 11 | 25.075 | 19 | 14.0125 | 7 | 5.9 | 67 | 49.4125 | 3 | 2.2125 | RD: glossary | Joel | 2021-02-08 | r
2021-02-23 | 10 | 24.65 | 19 | 13.775 | 7 | 5.8 | 67 | 48.575 | 3 | 2.175 | funct req | Palani | 2021-02-08 | r
2021-02-24 | 9 | 24.225 | 19 | 13.5375 | 6 | 5.7 | 67 | 47.7375 | 3 | 2.1375 | future features | Joel | 2021-02-09 | r
2021-02-25 | 9 | 23.8 | 19 | 13.3 | 4 | 5.6 | 67 | 46.9 | 3 | 2.1 | Use Case: createAccount | Lexy | 2021-02-09 | r
2021-02-26 | 9 | 23.375 | 19 | 13.0625 | 4 | 5.5 | 67 | 46.0625 | 3 | 2.0625 | UC: Reserve_Spot | Lexy | 2021-02-10 | r
2021-02-27 | 8 | 22.95 | 18 | 12.825 | 4 | 5.4 | 67 | 45.225 | 3 | 2.025 | UC: Use_reservation | Lexy | 2021-02-10 | r
2021-02-28 | 8 | 22.525 | 18 | 12.5875 | 4 | 5.3 | 67 | 44.3875 | 3 | 1.9875 | UC: Add_lot | Lexy | 2021-02-10 | r
2021-03-01 | 7 | 22.1 | 16 | 12.35 | 3 | 5.2 | 67 | 43.55 | 3 | 1.95 | UC: Add_spot | Lexy | 2021-02-10 | r
2021-03-02 | 7 | 21.675 | 16 | 12.1125 | 3 | 5.1 | 67 | 42.7125 | 3 | 1.9125 | UC: Open_lot | Lexy | 2021-02-10 | r
2021-03-03 | 7 | 21.25 | 14 | 11.875 | 1 | 5 | 67 | 41.875 | 3 | 1.875 | UC: Check_in | Lexy | 2021-02-10 | r
2021-03-04 | 7 | 20.825 | 14 | 11.6375 | 1 | 4.9 | 66 | 41.0375 | 3 | 1.8375 | UC: add event | Lexy | 2021-02-10 | r
2021-03-05 | 7 | 20.4 | 14 | 11.4 | 1 | 4.8 | 66 | 40.2 | 3 | 1.8 | RD: UML diagrams | Joel | 2021-02-10 | r
2021-03-06 | 7 | 19.975 | 14 | 11.1625 | 1 | 4.7 | 65 | 39.3625 | 3 | 1.7625 | Team org. | Autumn | 2021-02-12 | r
2021-03-07 | 7 | 19.55 | 14 | 10.925 | 1 | 4.6 | 65 | 38.525 | 3 | 1.725 | risk analysis | Autumn | 2021-02-11 | r
2021-03-08 | 7 | 19.125 | 14 | 10.6875 | 1 | 4.5 | 65 | 37.6875 | 3 | 1.6875 | build instructions | Palani | 2021-02-11 | r
2021-03-09 | 7 | 18.7 | 13 | 10.45 | 1 | 4.4 | 64 | 36.85 | 3 | 1.65 | testing instructions | Palani | 2021-02-11 | r
2021-03-10 | 7 | 18.275 | 9 | 10.2125 | 0 | 4.3 | 64 | 36.0125 | 3 | 1.6125 | Use case descriptions | Lexy | 2021-02-23 | r
2021-03-11 | 7 | 17.85 | 9 | 9.975 | 0 | 4.2 | 63 | 35.175 | 3 | 1.575 | funct req: update | Palani | 2021-02-24 | r
2021-03-12 | 7 | 17.425 | 9 | 9.7375 | 0 | 4.1 | 63 | 34.3375 | 3 | 1.5375 | Sign_up wireframe | Joel | 2021-02-24 | l
2021-03-13 | 7 | 17 | 9 | 9.5 | 0 | 4 | 63 | 33.5 | 3 | 1.5 | low prototype #2 | Joel | 2021-02-25 | l
2021-03-14 | 7 | 16.575 | 9 | 9.2625 | 0 | 3.9 | 63 | 32.6625 | 3 | 1.4625 | low prototype #3 | Joel | 2021-02-25 | l
2021-03-15 | 6 | 16.15 | 8 | 9.025 | 0 | 3.8 | 63 | 31.825 | 3 | 1.425 | maps | Palani | 2021-02-27 | h
2021-03-16 | 6 | 15.725 | 4 | 8.7875 | 0 | 3.7 | 63 | 30.9875 | 3 | 1.3875 | Activity diagrams | Autumn | 2021-02-27 | r
2021-03-17 | 6 | 15.3 | 3 | 8.55 | 0 | 3.6 | 62 | 30.15 | 3 | 1.35 | class diagram | Autumn | 2021-03-01 | l
2021-03-18 | 6 | 14.875 | 3 | 8.3125 | 0 | 3.5 | 55 | 29.3125 | 3 | 1.3125 | MS 2 - finalize scrum | Joel | 2021-03-01 | r
2021-03-19 | 6 | 14.45 | 2 | 8.075 | 0 | 3.4 | 55 | 28.475 | 3 | 1.275 | hi-proto to django | Palani | 2021-03-01 | h
2021-03-20 | 6 | 14.025 | 2 | 7.8375 | 0 | 3.3 | 55 | 27.6375 | 3 | 1.2375 | map marker | Palani | 2021-03-01 | h
2021-03-21 | 6 | 13.6 | 2 | 7.6 | 0 | 3.2 | 55 | 26.8 | 3 | 1.2 | initialize django proj | Palani | 2021-03-03 | h
2021-03-22 | 6 | 13.175 | 2 | 7.3625 | 0 | 3.1 | 52 | 25.9625 | 3 | 1.1625 | create apis app | Palani | 2021-03-03 | h
2021-03-23 | 6 | 12.75 | 2 | 7.125 | 0 | 3 | 50 | 25.125 | 3 | 1.125 | pastReservations.html | Joel | 2021-03-16 | h
2021-03-24 | 6 | 12.325 | 1 | 6.8875 | 0 | 2.9 | 49 | 24.2875 | 3 | 1.0875 | attendant.html | Joel | 2021-03-16 | h
2021-03-25 | 6 | 11.9 | 1 | 6.65 | 0 | 2.8 | 49 | 23.45 | 3 | 1.05 | about.html | Lexy | 2021-03-24 | h
2021-03-26 | 6 | 11.475 | 1 | 6.4125 | 0 | 2.7 | 49 | 22.6125 | 3 | 1.0125 | eventManagement.html | Joel | 2021-03-16 | h
2021-03-27 | 6 | 11.05 | 1 | 6.175 | 0 | 2.6 | 48 | 21.775 | 3 | 0.975 | lotInfo.html | Joel | 2021-03-17 | h
2021-03-28 | 6 | 10.625 | 1 | 5.9375 | 0 | 2.5 | 48 | 20.9375 | 3 | 0.9375 | ownerManagement.html | Joel | 2021-03-16 | h
2021-03-29 | 6 | 10.2 | 1 | 5.7 | 0 | 2.4 | 43 | 20.1 | 3 | 0.9 | lotManagement.html | Joel | 2021-03-19 | h
2021-03-30 | 6 | 9.775 | 1 | 5.4625 | 0 | 2.3 | 40 | 19.2625 | 3 | 0.8625 | Django: reserveSpot.html | Autumn | 2021-03-17 | d
2021-03-31 | 5 | 9.35 | 1 | 5.225 | 0 | 2.2 | 38 | 18.425 | 3 | 0.825 | Django: login.html | Autumn | 2021-03-18 | d
2021-04-01 | 5 | 8.925 | 1 | 4.9875 | 0 | 2.1 | 37 | 17.5875 | 3 | 0.7875 | Django: account.html | Autumn | 2021-03-18 | d
2021-04-02 | 5 | 8.5 | 1 | 4.75 | 0 | 2 | 37 | 16.75 | 3 | 0.75 | Django: main.html | Autumn | 2021-03-18 | d
2021-04-03 | 5 | 8.075 | 1 | 4.5125 | 0 | 1.9 | 37 | 15.9125 | 3 | 0.7125 | Django: pastReservations.html | Autumn | 2021-03-18 | d
2021-04-04 | 5 | 7.65 | 1 | 4.275 | 0 | 1.8 | 36 | 15.075 | 3 | 0.675 | Django: attendant.html | Autumn | 2021-03-18 | d
2021-04-05 | 5 | 7.225 | 1 | 4.0375 | 0 | 1.7 | 35 | 14.2375 | 3 | 0.6375 | Django: eventManagement.html | Autumn | 2021-03-18 | d
2021-04-06 | 5 | 6.8 | 1 | 3.8 | 0 | 1.6 | 35 | 13.4 | 3 | 0.6 | Django: ownerManagement.html | Autumn | 2021-03-18 | d
2021-04-07 | 5 | 6.375 | 1 | 3.5625 | 0 | 1.5 | 32 | 12.5625 | 3 | 0.5625 | Django: lotInfo.html | Autumn | 2021-03-22 | d
2021-04-08 | 5 | 5.95 | 1 | 3.325 | 0 | 1.4 | 31 | 11.725 | 3 | 0.525 | Django: lotManagement.html | Autumn | 2021-03-22 | d
2021-04-09 | 5 | 5.525 | 1 | 3.0875 | 0 | 1.3 | 30 | 10.8875 | 3 | 0.4875 | Django: map.html | Palani | 2021-03-29 | d
2021-04-10 | 5 | 5.1 | 1 | 2.85 | 0 | 1.2 | 21 | 10.05 | 3 | 0.45 | Updated main.css file to Django | Joel | 2021-03-22 | d
2021-04-11 | 5 | 4.675 | 1 | 2.6125 | 0 | 1.1 | 21 | 9.2125 | 3 | 0.4125 | Complete functionality: Login.html | Joel | 2021-03-23 | d
2021-04-12 | 5 | 4.25 | 1 | 2.375 | 0 | 1 | 17 | 8.375 | 3 | 0.375 | Complete functionality: signUp.html | Joel | 2021-03-23 | d
2021-04-13 | 5 | 3.825 | 1 | 2.1375 | 0 | 0.9 | 17 | 7.5375 | 3 | 0.3375 | complete functionality: reserveSpot.html | Autumn | 2021-03-24 | d
2021-04-14 | 2 | 3.4 | 1 | 1.9 | 0 | 0.8 | 11 | 6.7 | 0 | 0.3 | Complete functionality: main.html | Joel | 2021-03-29 | d
2021-04-15 | 2 | 2.975 | 0 | 1.6625 | 0 | 0.7 | 8 | 5.8625 | 0 | 0.2625 | Get maps working on necessary pages | Palani | 2021-03-27 | d
2021-04-16 | 2 | 2.55 | 0 | 1.425 | 0 | 0.6 | 8 | 5.025 | 0 | 0.225 | Finish maps API | Palani | 2021-03-29 | d
2021-04-17 | 2 | 2.125 | 0 | 1.1875 | 0 | 0.5 | 6 | 4.1875 | 0 | 0.1875 | Maps Javascript | Palani | 2021-03-29 | d
2021-04-18 | 2 | 1.7 | 0 | 0.95 | 0 | 0.4 | 3 | 3.35 | 0 | 0.15 | Update models | Palani | 2021-03-29 | d
2021-04-19 | 0 | 1.275 | 0 | 0.7125 | 0 | 0.3 | 0 | 2.5125 | 0 | 0.1125 | user password change | Autumn | 2021-03-30 | d
2021-04-20 | 0 | 0.85 | 0 | 0.475 | 0 | 0.2 | 0 | 1.675 | 0 | 0.075 | Page links | Joel | 2021-03-30 | d
2021-04-21 | 0 | 0.425 | 0 | 0.2375 | 0 | 0.1 | 0 | 0.8375 | 0 | 0.0375 | attendant checkin dropdown | Joel | 2021-03-30 | d
[11 empty] | added burndown chart | Autumn | 2021-03-31 | r
[11 empty] | format previous reservations | Autumn | 2021-03-31 | d
[11 empty] | fix reservations | Joel | 2021-03-31 | d
[11 empty] | page links | Joel | 2021-04-01 | d
[11 empty] | finished main | Joel | 2021-04-04 | d
[11 empty] | register new lot | Joel | 2021-04-05 | d
[11 empty] | only upcoming events on main | Joel | 2021-04-07 | d
[11 empty] | admin add event | Autumn | 2021-04-07 | d
[11 empty] | reserve spot half done | Autumn | 2021-04-07 | d
[11 empty] | Django: about.html | Lexy | 2021-04-08 | d
[11 empty] | delete event | Autumn | 2021-04-09 | d
[11 empty] | lot-info | Joel | 2021-04-10 | d
[11 empty] | model revision | Autumn | 2021-04-10 | d
[11 empty] | lot data api | Palani | 2021-04-10 | d
[11 empty] | javascript for single lot map | Palani | 2021-04-10 | d
[11 empty] | lot-info view | Joel | 2021-04-10 | d
[11 empty] | update migrations | Joel | 2021-04-10 | d
[11 empty] | only upcoming events on home | autumn | 2021-04-10 | d
[11 empty] | updated models | Palani | 2021-04-10 | d
[11 empty] | lot-info | Palani | 2021-04-10 | d
[11 empty] | fixed links | Joel | 2021-04-12 | d
[11 empty] | new lot registration | Joel | 2021-04-12 | d
[11 empty] | lat/long bug fix | Joel | 2021-04-12 | d
[11 empty] | reserve again | Joel | 2021-04-12 | d
[11 empty] | time field for new events | Autumn | 2021-04-14 | d
[11 empty] | reserve spot checking | Autumn | 2021-04-14 | d
[11 empty] | calculate lat/long | Palani | 2021-04-14 | d
[11 empty] | MS 3 sprint 2 docs | Autumn | 2021-04-14 | r
[11 empty] | MS 3 sprint 1 docs | Lexy | 2021-04-14 | r
[11 empty] | MS 3 sprint 3 docs | Palani | 2021-04-14 | r
[11 empty] | testing files | Joel | 2021-04-14 | t
[11 empty] | fixed map.html links | Autumn | 2021-04-14 | d
[11 empty] | added revenue model | Autumn | 2021-04-14 | d
[11 empty] | testing requirements | Autumn | 2021-04-14 | t
[11 empty] | tesing pass/fail | Autumn | 2021-04-14 | t
[11 empty] | lot management lists lots | Lexy | 2021-04-14 | d
[11 empty] | lot management lists events | Lexy | 2021-04-15 | d
[11 empty] | lot management lists spots | Lexy | 2021-04-15 | d
[11 empty] | lotEdit.html | Lexy | 2021-04-15 | h
[11 empty] | update reservation totals | Joel | 2021-04-15 | d
[11 empty] | revenue logic | Autumn | 2021-04-17 | d
[11 empty] | attendant page working | Palani | 2021-04-17 | d
[11 empty] | edit lot address and name | Lexy | 2021-04-18 | d
[11 empty] | lotEdit add/remove events | Lexy | 2021-04-18 | d
[11 empty] | lotEdit change parking spots | Lexy | 2021-04-18 | d
[11 empty] | update readme | Joel | 2021-04-19 | r
[11 empty] | ownerManagement shows owners | Joel | 2021-04-19 | d
[11 empty] | OM view any lots | Joel | 2021-04-19 | d
[11 empty] | OM revoke owners | Joel | 2021-04-19 | d
[11 empty] | Burndown Chart | Lexy | 2021-04-19 | r

## Percentage Burndown
Burndown Chart: Big Blue's Parking Genie
| Requirements Gathering |  | High-level Design |  | Low-level Design |  | Development |  | Testing |  | Expected | Task | Name | Date completed | Type
Date | Tasks left | Percent left | Tasks left | Percent left | Tasks left | Percent left | Tasks left | Percent left | Tasks left | Percent left | Percent | login.html | Joel | 2021-03-10 | h
2021-02-01 | 34 | 100% | 19 | 100% | 8 | 100% | 67 | 100% | 3 | 100% | 100% | reserveSpot.html | Joel | 2021-03-10 | h
2021-02-02 | 33 | 97.06% | 19 | 100% | 7 | 87.5% | 67 | 100% | 3 | 100% | 98.75% | map.html | Joel | 2021-03-10 | h
2021-02-03 | 33 | 97.06% | 19 | 100% | 7 | 87.5% | 67 | 100% | 3 | 100% | 97.5% | signUp.html | Joel | 2021-03-09 | h
2021-02-04 | 31 | 91.18% | 19 | 100% | 7 | 87.5% | 67 | 100% | 3 | 100% | 96.25% | Html/Css template | Joel | 2021-03-10 | l
2021-02-05 | 29 | 85.29% | 19 | 100% | 7 | 87.5% | 67 | 100% | 3 | 100% | 95% | account.html | Joel | 2021-03-10 | h
2021-02-06 | 28 | 82.35% | 19 | 100% | 7 | 87.5% | 67 | 100% | 3 | 100% | 93.75% | get website template | Joel | 2021-03-03 | l
2021-02-07 | 28 | 82.35% | 19 | 100% | 7 | 87.5% | 67 | 100% | 3 | 100% | 92.5% | outline models | Autumn | 2021-03-03 | l
2021-02-08 | 25 | 73.53% | 19 | 100% | 7 | 87.5% | 67 | 100% | 3 | 100% | 91.25% | set up API | Palani | 2021-03-04 | d
2021-02-09 | 23 | 67.65% | 19 | 100% | 7 | 87.5% | 67 | 100% | 3 | 100% | 90% | signUp.html->django | Palani | 2021-03-11 | d
2021-02-10 | 15 | 44.12% | 19 | 100% | 7 | 87.5% | 67 | 100% | 3 | 100% | 88.75% | rough draft models | Autumn | 2021-03-06 | d
2021-02-11 | 12 | 35.29% | 19 | 100% | 7 | 87.5% | 67 | 100% | 3 | 100% | 87.5% | Update models | Palani | 2021-03-09 | d
2021-02-12 | 11 | 32.35% | 19 | 100% | 7 | 87.5% | 67 | 100% | 3 | 100% | 86.25% | nav/main.html | Joel | 2021-03-15 | h
2021-02-13 | 11 | 32.35% | 19 | 100% | 7 | 87.5% | 67 | 100% | 3 | 100% | 85% | Scrum notes for sprint | Lexy | 2021-03-15 | r
2021-02-14 | 11 | 32.35% | 19 | 100% | 7 | 87.5% | 67 | 100% | 3 | 100% | 83.75% | create repo | Palani | 2021-02-02 | l
2021-02-15 | 11 | 32.35% | 19 | 100% | 7 | 87.5% | 67 | 100% | 3 | 100% | 82.5% | added doc outlines | Palani | 2021-02-02 | r
2021-02-16 | 11 | 32.35% | 19 | 100% | 7 | 87.5% | 67 | 100% | 3 | 100% | 81.25% | update todo | Palani | 2021-02-04 | r
2021-02-17 | 11 | 32.35% | 19 | 100% | 7 | 87.5% | 67 | 100% | 3 | 100% | 80% | Req Def: intro/context | Joel | 2021-02-04 | r
2021-02-18 | 11 | 32.35% | 19 | 100% | 7 | 87.5% | 67 | 100% | 3 | 100% | 78.75% | Project overview | Autumn | 2021-02-05 | r
2021-02-19 | 11 | 32.35% | 19 | 100% | 7 | 87.5% | 67 | 100% | 3 | 100% | 77.5% | adjusted repo structure | P/J | 2021-02-05 | r
2021-02-20 | 11 | 32.35% | 19 | 100% | 7 | 87.5% | 67 | 100% | 3 | 100% | 76.25% | RD: Users and goals | Joel | 2021-02-06 | r
2021-02-21 | 11 | 32.35% | 19 | 100% | 7 | 87.5% | 67 | 100% | 3 | 100% | 75% | RD: non-funct req | Joel | 2021-02-08 | r
2021-02-22 | 11 | 32.35% | 19 | 100% | 7 | 87.5% | 67 | 100% | 3 | 100% | 73.75% | RD: glossary | Joel | 2021-02-08 | r
2021-02-23 | 10 | 29.41% | 19 | 100% | 7 | 87.5% | 67 | 100% | 3 | 100% | 72.5% | funct req | Palani | 2021-02-08 | r
2021-02-24 | 9 | 26.47% | 19 | 100% | 6 | 75% | 67 | 100% | 3 | 100% | 71.25% | future features | Joel | 2021-02-09 | r
2021-02-25 | 9 | 26.47% | 19 | 100% | 4 | 50% | 67 | 100% | 3 | 100% | 70% | Use Case: createAccount | Lexy | 2021-02-09 | r
2021-02-26 | 9 | 26.47% | 19 | 100% | 4 | 50% | 67 | 100% | 3 | 100% | 68.75% | UC: Reserve_Spot | Lexy | 2021-02-10 | r
2021-02-27 | 8 | 23.53% | 18 | 94.74% | 4 | 50% | 67 | 100% | 3 | 100% | 67.5% | UC: Use_reservation | Lexy | 2021-02-10 | r
2021-02-28 | 8 | 23.53% | 18 | 94.74% | 4 | 50% | 67 | 100% | 3 | 100% | 66.25% | UC: Add_lot | Lexy | 2021-02-10 | r
2021-03-01 | 7 | 20.59% | 16 | 84.21% | 3 | 37.5% | 67 | 100% | 3 | 100% | 65% | UC: Add_spot | Lexy | 2021-02-10 | r
2021-03-02 | 7 | 20.59% | 16 | 84.21% | 3 | 37.5% | 67 | 100% | 3 | 100% | 63.75% | UC: Open_lot | Lexy | 2021-02-10 | r
2021-03-03 | 7 | 20.59% | 14 | 73.68% | 1 | 12.5% | 67 | 100% | 3 | 100% | 62.5% | UC: Check_in | Lexy | 2021-02-10 | r
2021-03-04 | 7 | 20.59% | 14 | 73.68% | 1 | 12.5% | 66 | 98.51% | 3 | 100% | 61.25% | UC: add event | Lexy | 2021-02-10 | r
2021-03-05 | 7 | 20.59% | 14 | 73.68% | 1 | 12.5% | 66 | 98.51% | 3 | 100% | 60% | RD: UML diagrams | Joel | 2021-02-10 | r
2021-03-06 | 7 | 20.59% | 14 | 73.68% | 1 | 12.5% | 65 | 97.01% | 3 | 100% | 58.75% | Team org. | Autumn | 2021-02-12 | r
2021-03-07 | 7 | 20.59% | 14 | 73.68% | 1 | 12.5% | 65 | 97.01% | 3 | 100% | 57.5% | risk analysis | Autumn | 2021-02-11 | r
2021-03-08 | 7 | 20.59% | 14 | 73.68% | 1 | 12.5% | 65 | 97.01% | 3 | 100% | 56.25% | build instructions | Palani | 2021-02-11 | r
2021-03-09 | 7 | 20.59% | 13 | 68.42% | 1 | 12.5% | 64 | 95.52% | 3 | 100% | 55% | testing instructions | Palani | 2021-02-11 | r
2021-03-10 | 7 | 20.59% | 9 | 47.37% | 0 | 0% | 64 | 95.52% | 3 | 100% | 53.75% | Use case descriptions | Lexy | 2021-02-23 | r
2021-03-11 | 7 | 20.59% | 9 | 47.37% | 0 | 0% | 63 | 94.03% | 3 | 100% | 52.5% | funct req: update | Palani | 2021-02-24 | r
2021-03-12 | 7 | 20.59% | 9 | 47.37% | 0 | 0% | 63 | 94.03% | 3 | 100% | 51.25% | Sign_up wireframe | Joel | 2021-02-24 | l
2021-03-13 | 7 | 20.59% | 9 | 47.37% | 0 | 0% | 63 | 94.03% | 3 | 100% | 50% | low prototype #2 | Joel | 2021-02-25 | l
2021-03-14 | 7 | 20.59% | 9 | 47.37% | 0 | 0% | 63 | 94.03% | 3 | 100% | 48.75% | low prototype #3 | Joel | 2021-02-25 | l
2021-03-15 | 6 | 17.65% | 8 | 42.11% | 0 | 0% | 63 | 94.03% | 3 | 100% | 47.5% | maps | Palani | 2021-02-27 | h
2021-03-16 | 6 | 17.65% | 4 | 21.05% | 0 | 0% | 63 | 94.03% | 3 | 100% | 46.25% | Activity diagrams | Autumn | 2021-02-27 | r
2021-03-17 | 6 | 17.65% | 3 | 15.79% | 0 | 0% | 62 | 92.54% | 3 | 100% | 45% | class diagram | Autumn | 2021-03-01 | l
2021-03-18 | 6 | 17.65% | 3 | 15.79% | 0 | 0% | 55 | 82.09% | 3 | 100% | 43.75% | MS 2 - finalize scrum | Joel | 2021-03-01 | r
2021-03-19 | 6 | 17.65% | 2 | 10.53% | 0 | 0% | 55 | 82.09% | 3 | 100% | 42.5% | hi-proto to django | Palani | 2021-03-01 | h
2021-03-20 | 6 | 17.65% | 2 | 10.53% | 0 | 0% | 55 | 82.09% | 3 | 100% | 41.25% | map marker | Palani | 2021-03-01 | h
2021-03-21 | 6 | 17.65% | 2 | 10.53% | 0 | 0% | 55 | 82.09% | 3 | 100% | 40% | initialize django proj | Palani | 2021-03-03 | h
2021-03-22 | 6 | 17.65% | 2 | 10.53% | 0 | 0% | 52 | 77.61% | 3 | 100% | 38.75% | create apis app | Palani | 2021-03-03 | h
2021-03-23 | 6 | 17.65% | 2 | 10.53% | 0 | 0% | 50 | 74.63% | 3 | 100% | 37.5% | pastReservations.html | Joel | 2021-03-16 | h
2021-03-24 | 6 | 17.65% | 1 | 5.263% | 0 | 0% | 49 | 73.13% | 3 | 100% | 36.25% | attendant.html | Joel | 2021-03-16 | h
2021-03-25 | 6 | 17.65% | 1 | 5.263% | 0 | 0% | 49 | 73.13% | 3 | 100% | 35% | about.html | Lexy | 2021-03-24 | h
2021-03-26 | 6 | 17.65% | 1 | 5.263% | 0 | 0% | 49 | 73.13% | 3 | 100% | 33.75% | eventManagement.html | Joel | 2021-03-16 | h
2021-03-27 | 6 | 17.65% | 1 | 5.263% | 0 | 0% | 48 | 71.64% | 3 | 100% | 32.5% | lotInfo.html | Joel | 2021-03-17 | h
2021-03-28 | 6 | 17.65% | 1 | 5.263% | 0 | 0% | 48 | 71.64% | 3 | 100% | 31.25% | ownerManagement.html | Joel | 2021-03-16 | h
2021-03-29 | 6 | 17.65% | 1 | 5.263% | 0 | 0% | 43 | 64.18% | 3 | 100% | 30% | lotManagement.html | Joel | 2021-03-19 | h
2021-03-30 | 6 | 17.65% | 1 | 5.263% | 0 | 0% | 40 | 59.7% | 3 | 100% | 28.75% | Django: reserveSpot.html | Autumn | 2021-03-17 | d
2021-03-31 | 5 | 14.71% | 1 | 5.263% | 0 | 0% | 38 | 56.72% | 3 | 100% | 27.5% | Django: login.html | Autumn | 2021-03-18 | d
2021-04-01 | 5 | 14.71% | 1 | 5.263% | 0 | 0% | 37 | 55.22% | 3 | 100% | 26.25% | Django: account.html | Autumn | 2021-03-18 | d
2021-04-02 | 5 | 14.71% | 1 | 5.263% | 0 | 0% | 37 | 55.22% | 3 | 100% | 25% | Django: main.html | Autumn | 2021-03-18 | d
2021-04-03 | 5 | 14.71% | 1 | 5.263% | 0 | 0% | 37 | 55.22% | 3 | 100% | 23.75% | Django: pastReservations.html | Autumn | 2021-03-18 | d
2021-04-04 | 5 | 14.71% | 1 | 5.263% | 0 | 0% | 36 | 53.73% | 3 | 100% | 22.5% | Django: attendant.html | Autumn | 2021-03-18 | d
2021-04-05 | 5 | 14.71% | 1 | 5.263% | 0 | 0% | 35 | 52.24% | 3 | 100% | 21.25% | Django: eventManagement.html | Autumn | 2021-03-18 | d
2021-04-06 | 5 | 14.71% | 1 | 5.263% | 0 | 0% | 35 | 52.24% | 3 | 100% | 20% | Django: ownerManagement.html | Autumn | 2021-03-18 | d
2021-04-07 | 5 | 14.71% | 1 | 5.263% | 0 | 0% | 32 | 47.76% | 3 | 100% | 18.75% | Django: lotInfo.html | Autumn | 2021-03-22 | d
2021-04-08 | 5 | 14.71% | 1 | 5.263% | 0 | 0% | 31 | 46.27% | 3 | 100% | 17.5% | Django: lotManagement.html | Autumn | 2021-03-22 | d
2021-04-09 | 5 | 14.71% | 1 | 5.263% | 0 | 0% | 30 | 44.78% | 3 | 100% | 16.25% | Django: map.html | Palani | 2021-03-29 | d
2021-04-10 | 5 | 14.71% | 1 | 5.263% | 0 | 0% | 21 | 31.34% | 3 | 100% | 15% | Updated main.css file to Django | Joel | 2021-03-22 | d
2021-04-11 | 5 | 14.71% | 1 | 5.263% | 0 | 0% | 21 | 31.34% | 3 | 100% | 13.75% | Complete functionality: Login.html | Joel | 2021-03-23 | d
2021-04-12 | 5 | 14.71% | 1 | 5.263% | 0 | 0% | 17 | 25.37% | 3 | 100% | 12.5% | Complete functionality: signUp.html | Joel | 2021-03-23 | d
2021-04-13 | 5 | 14.71% | 1 | 5.263% | 0 | 0% | 17 | 25.37% | 3 | 100% | 11.25% | complete functionality: reserveSpot.html | Autumn | 2021-03-24 | d
2021-04-14 | 2 | 5.882% | 1 | 5.263% | 0 | 0% | 11 | 16.42% | 0 | 0% | 10% | Complete functionality: main.html | Joel | 2021-03-29 | d
2021-04-15 | 2 | 5.882% | 0 | 0% | 0 | 0% | 8 | 11.94% | 0 | 0% | 8.75% | Get maps working on necessary pages | Palani | 2021-03-27 | d
2021-04-16 | 2 | 5.882% | 0 | 0% | 0 | 0% | 8 | 11.94% | 0 | 0% | 7.5% | Finish maps API | Palani | 2021-03-29 | d
2021-04-17 | 2 | 5.882% | 0 | 0% | 0 | 0% | 6 | 8.955% | 0 | 0% | 6.25% | Maps Javascript | Palani | 2021-03-29 | d
2021-04-18 | 2 | 5.882% | 0 | 0% | 0 | 0% | 3 | 4.478% | 0 | 0% | 5% | Update models | Palani | 2021-03-29 | d
2021-04-19 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 3.75% | user password change | Autumn | 2021-03-30 | d
2021-04-20 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 2.5% | Page links | Joel | 2021-03-30 | d
2021-04-21 | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 0 | 0% | 1.25% | attendant checkin dropdown | Joel | 2021-03-30 | d
[12 empty] | added burndown chart | Autumn | 2021-03-31 | r
[12 empty] | format previous reservations | Autumn | 2021-03-31 | d
[12 empty] | fix reservations | Joel | 2021-03-31 | d
[12 empty] | page links | Joel | 2021-04-01 | d
[12 empty] | finished main | Joel | 2021-04-04 | d
[12 empty] | register new lot | Joel | 2021-04-05 | d
[12 empty] | only upcoming events on main | Joel | 2021-04-07 | d
[12 empty] | admin add event | Autumn | 2021-04-07 | d
[12 empty] | reserve spot half done | Autumn | 2021-04-07 | d
[12 empty] | Django: about.html | Lexy | 2021-04-08 | d
[12 empty] | delete event | Autumn | 2021-04-09 | d
[12 empty] | lot-info | Joel | 2021-04-10 | d
[12 empty] | model revision | Autumn | 2021-04-10 | d
[12 empty] | lot data api | Palani | 2021-04-10 | d
[12 empty] | javascript for single lot map | Palani | 2021-04-10 | d
[12 empty] | lot-info view | Joel | 2021-04-10 | d
[12 empty] | update migrations | Joel | 2021-04-10 | d
[12 empty] | only upcoming events on home | autumn | 2021-04-10 | d
[12 empty] | updated models | Palani | 2021-04-10 | d
[12 empty] | lot-info | Palani | 2021-04-10 | d
[12 empty] | fixed links | Joel | 2021-04-12 | d
[12 empty] | new lot registration | Joel | 2021-04-12 | d
[12 empty] | lat/long bug fix | Joel | 2021-04-12 | d
[12 empty] | reserve again | Joel | 2021-04-12 | d
[12 empty] | time field for new events | Autumn | 2021-04-14 | d
[12 empty] | reserve spot checking | Autumn | 2021-04-14 | d
[12 empty] | calculate lat/long | Palani | 2021-04-14 | d
[12 empty] | MS 3 sprint 2 docs | Autumn | 2021-04-14 | r
[12 empty] | MS 3 sprint 1 docs | Lexy | 2021-04-14 | r
[12 empty] | MS 3 sprint 3 docs | Palani | 2021-04-14 | r
[12 empty] | testing files | Joel | 2021-04-14 | t
[12 empty] | fixed map.html links | Autumn | 2021-04-14 | d
[12 empty] | added revenue model | Autumn | 2021-04-14 | d
[12 empty] | testing requirements | Autumn | 2021-04-14 | t
[12 empty] | tesing pass/fail | Autumn | 2021-04-14 | t
[12 empty] | lot management lists lots | Lexy | 2021-04-14 | d
[12 empty] | lot management lists events | Lexy | 2021-04-15 | d
[12 empty] | lot management lists spots | Lexy | 2021-04-15 | d
[12 empty] | lotEdit.html | Lexy | 2021-04-15 | h
[12 empty] | update reservation totals | Joel | 2021-04-15 | d
[12 empty] | revenue logic | Autumn | 2021-04-17 | d
[12 empty] | attendant page working | Palani | 2021-04-17 | d
[12 empty] | edit lot address and name | Lexy | 2021-04-18 | d
[12 empty] | lotEdit add/remove events | Lexy | 2021-04-18 | d
[12 empty] | lotEdit change parking spots | Lexy | 2021-04-18 | d
[12 empty] | update readme | Joel | 2021-04-19 | r
[12 empty] | ownerManagement shows owners | Joel | 2021-04-19 | d
[12 empty] | OM view any lots | Joel | 2021-04-19 | d
[12 empty] | OM revoke owners | Joel | 2021-04-19 | d
[12 empty] | Burndown Chart | Lexy | 2021-04-19 | r