## Point Burndown
Burndown Chart: Sprint 1 (March 1-15)
| Requirements Gathering | High-level Design | Low-level Design | Development | Testing | Task | Name | Date completed | Type
Date | Tasks left | Tasks left | Tasks left | Tasks left | Tasks left | login.html | Joel | 2021-03-10 | h
2021-02-01 | 33 | 19 | 8 | 67 | 3 | reserveSpot.html | Joel | 2021-03-10 | h
2021-02-02 | 32 | 19 | 7 | 67 | 3 | map.html | Joel | 2021-03-10 | h
2021-02-03 | 32 | 19 | 7 | 67 | 3 | signUp.html | Joel | 2021-03-09 | h
2021-02-04 | 30 | 19 | 7 | 67 | 3 | Html/Css template | Joel | 2021-03-10 | l
2021-02-05 | 28 | 19 | 7 | 67 | 3 | account.html | Joel | 2021-03-10 | h
2021-02-06 | 27 | 19 | 7 | 67 | 3 | get website template | Joel | 2021-03-03 | l
2021-02-07 | 27 | 19 | 7 | 67 | 3 | outline models | Autumn | 2021-03-03 | l
2021-02-08 | 24 | 19 | 7 | 67 | 3 | set up API | Palani | 2021-03-04 | d
2021-02-09 | 22 | 19 | 7 | 67 | 3 | signUp.html->django | Palani | 2021-03-11 | d
2021-02-10 | 14 | 19 | 7 | 67 | 3 | rough draft models | Autumn | 2021-03-06 | d
2021-02-11 | 11 | 19 | 7 | 67 | 3 | Update models | Palani | 2021-03-09 | d
2021-02-12 | 10 | 19 | 7 | 67 | 3 | nav/main.html | Joel | 2021-03-15 | h
2021-02-13 | 10 | 19 | 7 | 67 | 3 | Scrum notes for sprint | Lexy | 2021-03-15 | r
2021-02-14 | 10 | 19 | 7 | 67 | 3 | create repo | Palani | 2021-02-02 | l
2021-02-15 | 10 | 19 | 7 | 67 | 3 | added doc outlines | Palani | 2021-02-02 | r
2021-02-16 | 10 | 19 | 7 | 67 | 3 | update todo | Palani | 2021-02-04 | r
2021-02-17 | 10 | 19 | 7 | 67 | 3 | Req Def: intro/context | Joel | 2021-02-04 | r
2021-02-18 | 10 | 19 | 7 | 67 | 3 | Project overview | Autumn | 2021-02-05 | r
2021-02-19 | 10 | 19 | 7 | 67 | 3 | adjusted repo structure | P/J | 2021-02-05 | r
2021-02-20 | 10 | 19 | 7 | 67 | 3 | RD: Users and goals | Joel | 2021-02-06 | r
2021-02-21 | 10 | 19 | 7 | 67 | 3 | RD: non-funct req | Joel | 2021-02-08 | r
2021-02-22 | 10 | 19 | 7 | 67 | 3 | RD: glossary | Joel | 2021-02-08 | r
2021-02-23 | 9 | 19 | 7 | 67 | 3 | funct req | Palani | 2021-02-08 | r
2021-02-24 | 8 | 19 | 6 | 67 | 3 | future features | Joel | 2021-02-09 | r
2021-02-25 | 8 | 19 | 4 | 67 | 3 | Use Case: createAccount | Lexy | 2021-02-09 | r
2021-02-26 | 8 | 19 | 4 | 67 | 3 | UC: Reserve_Spot | Lexy | 2021-02-10 | r
2021-02-27 | 7 | 18 | 4 | 67 | 3 | UC: Use_reservation | Lexy | 2021-02-10 | r
2021-02-28 | 7 | 18 | 4 | 67 | 3 | UC: Add_lot | Lexy | 2021-02-10 | r
2021-03-01 | 6 | 16 | 3 | 67 | 3 | UC: Add_spot | Lexy | 2021-02-10 | r
2021-03-02 | 6 | 16 | 3 | 67 | 3 | UC: Open_lot | Lexy | 2021-02-10 | r
2021-03-03 | 6 | 14 | 1 | 67 | 3 | UC: Check_in | Lexy | 2021-02-10 | r
2021-03-04 | 6 | 14 | 1 | 66 | 3 | UC: add event | Lexy | 2021-02-10 | r
2021-03-05 | 6 | 14 | 1 | 66 | 3 | RD: UML diagrams | Joel | 2021-02-10 | r
2021-03-06 | 6 | 14 | 1 | 65 | 3 | Team org. | Autumn | 2021-02-12 | r
2021-03-07 | 6 | 14 | 1 | 65 | 3 | risk analysis | Autumn | 2021-02-11 | r
2021-03-08 | 6 | 14 | 1 | 65 | 3 | build instructions | Palani | 2021-02-11 | r
2021-03-09 | 6 | 13 | 1 | 64 | 3 | testing instructions | Palani | 2021-02-11 | r
2021-03-10 | 6 | 9 | 0 | 64 | 3 | Use case descriptions | Lexy | 2021-02-23 | r
2021-03-11 | 6 | 9 | 0 | 63 | 3 | funct req: update | Palani | 2021-02-24 | r
2021-03-12 | 6 | 9 | 0 | 63 | 3 | Sign_up wireframe | Joel | 2021-02-24 | l
2021-03-13 | 6 | 9 | 0 | 63 | 3 | low prototype #2 | Joel | 2021-02-25 | l
2021-03-14 | 6 | 9 | 0 | 63 | 3 | low prototype #3 | Joel | 2021-02-25 | l
2021-03-15 | 5 | 8 | 0 | 63 | 3 | maps | Palani | 2021-02-27 | h
2021-03-16 | 5 | 4 | 0 | 63 | 3 | Activity diagrams | Autumn | 2021-02-27 | r
2021-03-17 | 5 | 3 | 0 | 62 | 3 | class diagram | Autumn | 2021-03-01 | l
2021-03-18 | 5 | 3 | 0 | 55 | 3 | MS 2 - finalize scrum | Joel | 2021-03-01 | r
2021-03-19 | 5 | 2 | 0 | 55 | 3 | hi-proto to django | Palani | 2021-03-01 | h
2021-03-20 | 5 | 2 | 0 | 55 | 3 | map marker | Palani | 2021-03-01 | h
2021-03-21 | 5 | 2 | 0 | 55 | 3 | initialize django proj | Palani | 2021-03-03 | h
2021-03-22 | 5 | 2 | 0 | 52 | 3 | create apis app | Palani | 2021-03-03 | h
2021-03-23 | 5 | 2 | 0 | 50 | 3 | pastReservations.html | Joel | 2021-03-16 | h
2021-03-24 | 5 | 1 | 0 | 49 | 3 | attendant.html | Joel | 2021-03-16 | h
2021-03-25 | 5 | 1 | 0 | 49 | 3 | about.html | Lexy | 2021-03-24 | h
2021-03-26 | 5 | 1 | 0 | 49 | 3 | eventManagement.html | Joel | 2021-03-16 | h
2021-03-27 | 5 | 1 | 0 | 48 | 3 | lotInfo.html | Joel | 2021-03-17 | h
2021-03-28 | 5 | 1 | 0 | 48 | 3 | ownerManagement.html | Joel | 2021-03-16 | h
2021-03-29 | 5 | 1 | 0 | 43 | 3 | lotManagement.html | Joel | 2021-03-19 | h
2021-03-30 | 5 | 1 | 0 | 40 | 3 | Django: reserveSpot.html | Autumn | 2021-03-17 | d
2021-03-31 | 4 | 1 | 0 | 38 | 3 | Django: login.html | Autumn | 2021-03-18 | d
2021-04-01 | 4 | 1 | 0 | 37 | 3 | Django: account.html | Autumn | 2021-03-18 | d
2021-04-02 | 4 | 1 | 0 | 37 | 3 | Django: main.html | Autumn | 2021-03-18 | d
2021-04-03 | 4 | 1 | 0 | 37 | 3 | Django: pastReservations.html | Autumn | 2021-03-18 | d
2021-04-04 | 4 | 1 | 0 | 36 | 3 | Django: attendant.html | Autumn | 2021-03-18 | d
2021-04-05 | 4 | 1 | 0 | 35 | 3 | Django: eventManagement.html | Autumn | 2021-03-18 | d
2021-04-06 | 4 | 1 | 0 | 35 | 3 | Django: ownerManagement.html | Autumn | 2021-03-18 | d
2021-04-07 | 4 | 1 | 0 | 32 | 3 | Django: lotInfo.html | Autumn | 2021-03-22 | d
2021-04-08 | 4 | 1 | 0 | 31 | 3 | Django: lotManagement.html | Autumn | 2021-03-22 | d
2021-04-09 | 4 | 1 | 0 | 30 | 3 | Django: map.html | Palani | 2021-03-29 | d
2021-04-10 | 4 | 1 | 0 | 21 | 3 | Updated main.css file to Django | Joel | 2021-03-22 | d
2021-04-11 | 4 | 1 | 0 | 21 | 3 | Complete functionality: Login.html | Joel | 2021-03-23 | d
2021-04-12 | 4 | 1 | 0 | 17 | 3 | Complete functionality: signUp.html | Joel | 2021-03-23 | d
2021-04-13 | 4 | 1 | 0 | 17 | 3 | complete functionality: reserveSpot.html | Autumn | 2021-03-24 | d
2021-04-14 | 1 | 1 | 0 | 11 | 0 | Complete functionality: main.html | Joel | 2021-03-29 | d
2021-04-15 | 1 | 0 | 0 | 8 | 0 | Get maps working on necessary pages | Palani | 2021-03-27 | d
2021-04-16 | 1 | 0 | 0 | 8 | 0 | Finish maps API | Palani | 2021-03-29 | d
2021-04-17 | 1 | 0 | 0 | 6 | 0 | Maps Javascript | Palani | 2021-03-29 | d
2021-04-18 | 1 | 0 | 0 | 3 | 0 | Update models | Palani | 2021-03-29 | d
2021-04-19 | 0 | 0 | 0 | 0 | 0 | user password change | Autumn | 2021-03-30 | d
2021-04-20 | 0 | 0 | 0 | 0 | 0 | Page links | Joel | 2021-03-30 | d
2021-04-21 | 0 | 0 | 0 | 0 | 0 | attendant checkin dropdown | Joel | 2021-03-30 | d
[6 empty] | added burndown chart | Autumn | 2021-03-31 | r
[6 empty] | format previous reservations | Autumn | 2021-03-31 | d
[6 empty] | fix reservations | Joel | 2021-03-31 | d
[6 empty] | page links | Joel | 2021-04-01 | d
[6 empty] | finished main | Joel | 2021-04-04 | d
[6 empty] | register new lot | Joel | 2021-04-05 | d
[6 empty] | only upcoming events on main | Joel | 2021-04-07 | d
[6 empty] | admin add event | Autumn | 2021-04-07 | d
[6 empty] | reserve spot half done | Autumn | 2021-04-07 | d
[6 empty] | Django: about.html | Lexy | 2021-04-08 | d
[6 empty] | delete event | Autumn | 2021-04-09 | d
[6 empty] | lot-info | Joel | 2021-04-10 | d
[6 empty] | model revision | Autumn | 2021-04-10 | d
[6 empty] | lot data api | Palani | 2021-04-10 | d
[6 empty] | javascript for single lot map | Palani | 2021-04-10 | d
[6 empty] | lot-info view | Joel | 2021-04-10 | d
[6 empty] | update migrations | Joel | 2021-04-10 | d
[6 empty] | only upcoming events on home | autumn | 2021-04-10 | d
[6 empty] | updated models | Palani | 2021-04-10 | d
[6 empty] | lot-info | Palani | 2021-04-10 | d
[6 empty] | fixed links | Joel | 2021-04-12 | d
[6 empty] | new lot registration | Joel | 2021-04-12 | d
[6 empty] | lat/long bug fix | Joel | 2021-04-12 | d
[6 empty] | reserve again | Joel | 2021-04-12 | d
[6 empty] | time field for new events | Autumn | 2021-04-14 | d
[6 empty] | reserve spot checking | Autumn | 2021-04-14 | d
[6 empty] | calculate lat/long | Palani | 2021-04-14 | d
[6 empty] | MS 3 sprint 2 docs | Autumn | 2021-04-14 | r
[6 empty] | MS 3 sprint 1 docs | Lexy | 2021-04-14 | r
[6 empty] | MS 3 sprint 3 docs | Palani | 2021-04-14 | r
[6 empty] | testing files | Joel | 2021-04-14 | t
[6 empty] | fixed map.html links | Autumn | 2021-04-14 | d
[6 empty] | added revenue model | Autumn | 2021-04-14 | d
[6 empty] | testing requirements | Autumn | 2021-04-14 | t
[6 empty] | tesing pass/fail | Autumn | 2021-04-14 | t
[6 empty] | lot management lists lots | Lexy | 2021-04-14 | d
[6 empty] | lot management lists events | Lexy | 2021-04-15 | d
[6 empty] | lot management lists spots | Lexy | 2021-04-15 | d
[6 empty] | lotEdit.html | Lexy | 2021-04-15 | h
[6 empty] | update reservation totals | Joel | 2021-04-15 | d
[6 empty] | revenue logic | Autumn | 2021-04-17 | d
[6 empty] | attendant page working | Palani | 2021-04-17 | d
[6 empty] | edit lot address and name | Lexy | 2021-04-18 | d
[6 empty] | lotEdit add/remove events | Lexy | 2021-04-18 | d
[6 empty] | lotEdit change parking spots | Lexy | 2021-04-18 | d
[6 empty] | update readme | Joel | 2021-04-19 | r
[6 empty] | ownerManagement shows owners | Joel | 2021-04-19 | d
[6 empty] | OM view any lots | Joel | 2021-04-19 | d
[6 empty] | OM revoke owners | Joel | 2021-04-19 | d