## Progress Tracker
SCRUM MEETING BOARD - Group10 The Djinns
| Big Blue's Parking Genie | SPRINT LEADER | START DATE | END DATE |  | OVERALL PROGRESS
|  | Joel C. | 2021-02-23 | 2021-03-01
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Milestone2: Sprint 1 | [6 empty] | In Progress
| Low Fidelity Prototype 1 | Sign Up Page Wireframe | Joel C. |  | 2021-02-23 | 2021-02-24 | 1 | Complete | https://github.com/palani-johnson/TheDjinns-Group10/blob/main/docs/Prototypes/lowFidelity1_SignUpWireFrame.png
| Low Fidelity Prototype 2 | Customer Navigation Wireframe | Joel C. |  | 2021-02-24 | 2021-02-25 | 1 | Complete | https://github.com/palani-johnson/TheDjinns-Group10/blob/main/docs/Prototypes/lowFidelity2_CustomerNavigationWireframe.png
| Low Fidelity Prototype 3 | Customer Account Wireframe | Joel C. |  | 2021-02-24 | 2021-02-25 | 1 | Complete | https://github.com/palani-johnson/TheDjinns-Group10/blob/main/docs/Prototypes/lowFidelity3_CustomerAccountWireframe.png
| High Fidelity Prototype |  | Palani J. |  | 2021-02-23 | 2021-03-01 | 6 | In Progress
| Sprint Backlog Work |  | Lexy S. |  | 2021-02-23 | 2021-03-01 | 6 | In Progress
| Activity/Class Diagrams |  | Autumn A. |  | 2021-02-23 | 2021-03-01 | 6 | In Progress

## Standup Meetings Scrum Board
Scrum Board
2021-02-23
Planning Meeting Notes:
Mtg 1: Sprint Planning 2/23/21 5:00pm - Agenda: Update/talk about GitHub Know the Beginning from the End Sprint due date: Monday -- March 1, 2021 Mtg TODO: - Estimate how many hours we have to work on this project this sprint? ~8 hr each? - Discuss availability - Discuss using milestone project points again as metric 17.5 Canvas points per person TOTAL -16 for milestone 1 revisions divied up as described below 54 / 4 = 13.5 points per person *Each person revise their specific documents from Milestone 1 as needed Revisions to milestone 1 risk analysis use case info sheets functional requirements numbering - Discuss improvements from last sprint - Assign ProjectLeader/ScrumMaster for this sprint (Milestone 2) Filling out details for stories (big picture tasks) After-mtg Tasks: - JOEL: Organize Milestones, Sprints, Tasks/Stories for GitHub moving forward - JOEL: Add all previous stories (big picture tasks) to Done column of GitHub Mtg TODO: - List stories for the sprint - Describe each of following for each story/task 1. Size estimate (pts, S/M/L) 2. Description of scope (in/out of) 3. Acceptance criteria for completion 4. List tasks for this story to be completed - created in GitHub as notes (then convert to issues assigned to a person) - assign size estimate to each (pts, S/M/L) Immediate Tasks: - JOEL: 1. Create Spring Backlog and Organize GitHub repo with Milestones, Sprints, Tasks/Stories 2. Add all previous TODO tasks to Done column of GitHub - PALANI: 1. Add in old tasks from TODOs and read commit history to ?backdate? issues 2. - Ask about in class: Use Case diagrams on Rubric - existing or new? Difference in Product Backlog requirements in Rubric Sprint Stories(to be filled out in mtg): 1. Example Story 1. Size estimate (pts, S/M/L) 2. Description of scope (in/out of) 3. Acceptance criteria for completion 4. List tasks for this story to be completed - created in GitHub as notes (then convert to issues assigned to a person) - assign size estimate to each (pts, S/M/L) PROTOTYPES: High Google maps api page Low wireframe outlining different Django views Joel - Low fidelity Lexy - Backlog Palani - Add past backlog commits to GitHub, High fidelity Autumn - Diagrams Product Backlog in GitHub repo issues (12) Stories? 10+ items (10pts) small items (2) * ask about difference in class README revisions project plan revisiosn req def revisions SAME ASSIGNMENTS AS MILESTONE 1 use case diagrams (4) ask about in class class diagrams (6) activity diagrams (6) high fidelity prototypes (12) google maps page? low fidelity prototype (10) history on scrum board showing who is working which items and when they are completed (4)
2021-02-24 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | Completed 1st low fidelity prototype: Sign Up page wireframe | Complete 2nd wireframe, fill out scrum board, log hours, etc | Questions about design of navigation page for each user | Notes:
| Lexy S. | Reviewed Sprint Backlog and milestone 2 requirements | Add all requirements for Milestone 2 to Project Board/Sprint Backlog | Knowing scope of cards to add to Backlog | Joel -- Finish 2nd low fidelity wireframe Palani -- Add Django high fidelity prototype Lexy -- Get Milestone 2 backlog entries filled in Autumn -- Get Started on Activity Diagrams Activities Attendant Checking in a Customer Owner Adds Attendant Manually via Username owner types in username Reserving a Spot * add a note this is high priority get event, get lot, get open spots **Document more high priority features or processes**
| Palani J. | Started working on high fidelity prototype | Continue work on prototype, get better understanding of Google maps API | How to implement Google maps API, using git branches
| Autumn A. | Beginning work with activity diagrams | Complete some activity diagrams | Which activities to diagram?
2021-02-25 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
in class | Joel C. | Created this excel sheet | Finish low fidelity wireframes 2/3, start thinking about design of model classes/database | Knowing what classes are necessary for the database…
| Lexy S. | Added Milestone 2 items to Sprint Backlog | Add Milestone 1 cards to Sprint Backlog, breakup current items to be 1-2 workday size | Additional Future To Do column? What items to add?
| Palani J. | n/a | n/a | absent
| Autumn A. | Working with Visal Paradigm | Complete first draft Activity diagrams | What classes to diagram? What activites? Should certain activities be separate or as one larger diagram?
2021-02-25 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | 2 wireframes | Add previous reservations list to see spots you like, move current reservations tab to navigation page
| Lexy S. | see previous scrum mtg
| Palani J. | n/a | n/a | absent
| Autumn A. | 3 activity diagrams | start on class diagrams | GOOD JOB :)
2021-02-26 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | none | none
| Lexy S. | created new column in Backlog, 1 new issue | Milestone 1 cards
| Palani J. | high fidelity prototype | high fidelity prototype
| Autumn A. | none yet, more today | upload activity diagrams, work on class
2021-02-27 | Team Member | Progress since last scrum | To Do Before Next Scrum | Obstacles
standup | Joel C. | none | Finish wireframes, update progress tracker to match issues, etc on GitHub
| Lexy S. | Added ~40 issues to GitHub Sprint backlog, including past ones from Milestone 1 | Close milestone 1 issues/milestone
| Palani J. | Google Maps API started | Work more on high fidelity prototype
| Autumn A. | Worked on class diagrams | Finish class diagrams (questions about permissions vs different inherited user types | Questions about classes (good discussion)